RailSync Platform

Development Build Roadmap

Full CIPROTS Replacement — Sprint-by-Sprint Execution Plan

4-Person Team  |  20 Sprints  |  40 Weeks  |  3 Releases + Go-Live

Fleet Operations | AITX | February 2026

Team Structure & Roles

| Role | Focus Area | Responsibilities |
| --- | --- | --- |
| Dev 1 (BE) | Backend Lead | Database architecture, core business logic, state machines, billing engine, SAP integration, data migration |
| Dev 2 (BE) | Backend + Integration | Secondary backend, bulk operations, external integrations (Salesforce, CLM, Railinc), BRC processing, planning engine |
| Dev 3 (FE) | Frontend Lead | All UI components, pages, dashboards. React/TypeScript/Tailwind. Navigation, forms, data tables, charts, wizards |
| UI/QA Mgr | Quality + Process | Test strategy, CI/CD pipeline, code reviews, QA passes per sprint, stakeholder demos, training materials, go-live coordination |

Release Timeline

| Release | Sprints | Modules Delivered | Business Value |
| --- | --- | --- | --- |
| Release 1 | S1-S6 (Wk 1-12) | Car Master, Qualifications, Contracts, Assignments/Releases | Asset management foundation. Cars tracked with permanent identity. Leases managed. Quals drive scheduling. |
| Release 2 | S7-S12 (Wk 13-24) | Shopping Workflow, Projects, BRC Processing, Invoice Reconciliation, Cost Allocation | Full shop operations. Shopping authorized → completed → invoiced → allocated. Core CIPROTS operational replacement. |
| Release 3 | S13-S18 (Wk 25-36) | Billing, SAP/SF/CLM Integration, S&OP Planning, Reporting, Data Migration, Parallel Run | Monthly billing automated. External systems connected. Planning capability live. Migration validated. |
| Go-Live | S19-S20 (Wk 37-40) | Cutover, Stabilization, Training | CIPROTS retired. RailSync Platform is operational SSoT for AITX Fleet Operations. |

Tech Stack (Existing — No Changes)

Frontend: React 18 + TypeScript + Vite + TailwindCSS + Recharts  |  Backend: Node.js + Express + TypeScript + Prisma ORM  |  Database: PostgreSQL  |  Auth: JWT + RBAC  |  DevOps: Docker + GitHub Actions

Sprint-by-Sprint Execution Plan

Each sprint = 2 weeks. Every team member has assigned deliverables per sprint. Tasks are ordered by dependency — work items at the top of each sprint should start first.

| RELEASE 1: FOUNDATION (Sprints 1-6 ¦ Weeks 1-12) |  |  |
| --- | --- | --- |

| SPRINT 1 ¦ Weeks 1-2 ¦ Architecture + Car Master Schema |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Database architecture: PostgreSQL schema design, migration framework, Prisma model updates | Dev 1 (BE) | schema.prisma with cars, car_mark_history, spvs, components tables. Migration files. |
| Permanent car identity: UUID generation, immutable ID constraints, road mark history tracking | Dev 1 (BE) | Car CRUD API: POST/GET/PUT. car_mark_history with date ranges. |
| SPV entity: 30-40 SPVs, car-to-SPV ownership, transfer history with audit trail | Dev 2 (BE) | SPV CRUD API. Transfer endpoint with history logging. |
| Car physical attributes: AAR type, build date, manufacturer, jacketed/lined flags, shell specs | Dev 2 (BE) | Car detail fields added to schema and API. |
| Navigation architecture: app shell, routing, sidebar, role-based menu system | Dev 3 (FE) | App layout with placeholder pages for all modules. Routing configured. |
| UI component library: data tables, form components, search bars, status badges, card layouts | Dev 3 (FE) | Shared component library: DataTable, SearchInput, StatusBadge, FormField, Card. |
| QA environment setup: test framework, CI pipeline, code review process, branching strategy | UI/QA Mgr | Jest + React Testing Library configured. GitHub Actions CI. PR template. |

| SPRINT 2 ¦ Weeks 3-4 ¦ Car Master UI + Car Status Engine |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Car status model: On Lease, In Storage, In Shop, Mobile Repair, Bad Order, In Transit. Transition rules and validation. | Dev 1 (BE) | Status enum + state machine service. Transition validation middleware. |
| Component registry: serial number tracking for valves, BOVs, fittings. Component-level maintenance history. | Dev 1 (BE) | components table, component_history table. CRUD API with serial number validation. |
| Bulk import engine: CSV/Excel parsing, validation pipeline, duplicate detection, error reporting. | Dev 2 (BE) | POST /cars/bulk-import. Accepts CSV/XLSX. Returns validation report with row-level errors. |
| Car search + detail page: search by permanent ID, road mark, customer, SPV. Tabbed detail view. | Dev 3 (FE) | CarSearch page + CarDetail page with tabs: General, Components, History, Qualifications. |
| Car registration form: new car entry, SPV assignment, initial status. Validation. | Dev 3 (FE) | CarRegistration form with field validation. Success/error feedback. |
| Remark / transfer UI: road mark change form, SPV transfer form. History display. | Dev 3 (FE) | RemarkDialog + TransferDialog components. HistoryTimeline component. |
| Car master QA: test all CRUD operations, bulk import edge cases, status transitions. | UI/QA Mgr | Test suite for car API. UI test scripts. Bug tracking board initialized. |

| 🏁 MILESTONE: CAR MASTER MVP — Cars can be registered, searched, transferred, imported. Foundation for all modules. |  |  |
| --- | --- | --- |

| SPRINT 3 ¦ Weeks 5-6 ¦ Qualifications + Compliance Engine |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Qualification data model: types (tank requalification, air brake, safety appliance, hazmat), intervals, status calc. | Dev 1 (BE) | qualifications table. Qualification types config. Status calculation service (Current/Due/Overdue). |
| Compliance alerting engine: 90/60/30-day warnings, overdue escalation, batch calculation for fleet. | Dev 1 (BE) | Scheduled job: calculate_qualification_status. Alert generation. GET /qualifications/alerts. |
| Qual-to-scheduling link: qualification due dates feed RailSync priority scoring. Cars due sooner score higher. | Dev 2 (BE) | Integration point: RailSync evaluateCar() now accepts qual_due_date and weights it in scoring. |
| Bulk qualification update: range update for groups of cars. Regulatory validation on date changes. | Dev 2 (BE) | POST /qualifications/bulk-update. Validates against regulatory interval rules. |
| Qualification dashboard: fleet-wide status, cars due by month, overdue list. Filter by type, SPV, customer. | Dev 3 (FE) | QualificationDashboard page: KPI cards, due-by-month chart, overdue table with filters. |
| Per-car qualification tab: all qualification types, dates, next due, completion history. | Dev 3 (FE) | QualificationTab component (plugs into CarDetail). QualificationUpdateForm. |
| Qualification QA: test interval calculations, alerting thresholds, bulk update validation. | UI/QA Mgr | Test matrix for all qualification types. Edge case tests (expired, near-expiry, exempt). |

| SPRINT 4 ¦ Weeks 7-8 ¦ Contracts + Lease Management |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Lease/contract data model: Master + Rider structure. Contract number, version, effective dates, renewal terms. | Dev 1 (BE) | leases, riders tables. Version management. CRUD API with validation. |
| Rider management: commodity per rider, terms, maintenance responsibility, rates. Commodity is lease-driven. | Dev 1 (BE) | riders CRUD. Commodity lookup from active rider (not car master). Rate management. |
| Car-to-lease assignment: many-to-many via riders. Activation dates, billing triggers. Full assignment history. | Dev 2 (BE) | lease_car_assignments table. Assign/release endpoints. History tracking. |
| Rate management: rental rates, escalations, abatements. Rate changes per version. | Dev 2 (BE) | rates table. Escalation calculation service. Abatement rules. |
| Renewal engine: detect expiring contracts, version management, partial renewals, car rollover. | Dev 2 (BE) | RenewalService: detect_expiring(), create_renewal_version(), rollover_cars(). |
| Contract search + detail UI: search by number, customer, car. Detail with riders, cars, rates, history. | Dev 3 (FE) | ContractSearch + ContractDetail pages. RiderPanel, AssignedCarsGrid, RateHistory. |
| Contract creation UI: streamlined form. Rider setup. Commodity and location entry. | Dev 3 (FE) | ContractCreateWizard: 3-step (Header → Riders → Cars). Validation at each step. |
| Contract QA: test renewal flows, rate calculations, car assignment/release. | UI/QA Mgr | Renewal scenario tests. Rate escalation validation. Assignment lifecycle tests. |

| 🏁 MILESTONE: CONTRACTS MVP — Leases created, riders with commodities, cars assigned, renewals working. Replaces CIPROTS Contracts module. |  |  |
| --- | --- | --- |

| SPRINT 5 ¦ Weeks 9-10 ¦ Assignments + Releases |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Pending assignments engine: cars tagged for contract assignment. Activation dates, rate application. | Dev 1 (BE) | pending_assignments table. Assignment queue. Activation service with billing trigger. |
| Release management: release from contracts. Type (storage, new customer, shop). Billing credit calc. | Dev 1 (BE) | ReleaseService: create_release(), calculate_credit(). Release-to-shopping trigger. |
| Contract transfers: move cars between contracts/versions. Source → destination with billing adjustments. | Dev 2 (BE) | TransferService: transfer_cars(). Auto-generate adjustment records. |
| Release → Shopping link: release triggers shopping authorization. Auto-populate type, scope, shop selection. | Dev 2 (BE) | Integration: release creates shopping_event with type=Release. RailSync shop recommendation attached. |
| Pending actions dashboard: all pending assignments and releases. Filter by customer, contract, date. Batch ops. | Dev 3 (FE) | PendingActions page: tabs for Assignments, Releases, Transfers. Batch action buttons. |
| Release workflow UI: select cars → set type → auto-select shop (RailSync) → create shopping. Streamlined. | Dev 3 (FE) | ReleaseWizard: 2-step (Select Cars → Confirm Shop + Scope). Replace 23-step CIPROTS wizard. |
| Assignment/release QA: lifecycle tests, billing trigger validation, transfer accuracy. | UI/QA Mgr | End-to-end scenario: create assignment → activate → release → shopping created. |

| SPRINT 6 ¦ Weeks 11-12 ¦ Release 1 Integration + Stabilization |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Cross-module integration: car status updates from assignments, releases, contract changes. Consistency checks. | Dev 1 (BE) | Integration tests across Car ↔ Contract ↔ Assignment ↔ Qualification modules. |
| Data migration script v1: migrate car master from CIPROTS + CIS. Map to permanent identity. Validate. | Dev 2 (BE) | Migration script: extract_ciprots_cars.py. Mapping rules. Validation report. |
| Performance optimization: database indexing, query optimization, pagination for large datasets. | Dev 2 (BE) | Index strategy document. Query profiling. API response < 200ms for standard queries. |
| Release 1 UI polish: consistent styling, loading states, error handling, empty states across all modules. | Dev 3 (FE) | UI review pass. Fix inconsistencies. Add skeleton loaders, error boundaries. |
| Seed data: realistic 1,000-car dataset with contracts, qualifications, SPVs for demo/testing. | Dev 3 (FE) | seed.ts update with realistic AITX data patterns. |
| Release 1 regression testing: full QA pass across all modules. Bug triage and fixes. | UI/QA Mgr | QA report. P1 bug count = 0. Known issues documented. |
| Stakeholder demo: show Fleet Ops the car master, qualifications, contracts, assignments. | UI/QA Mgr | Demo script prepared. Feedback collected and triaged. |

| 🏁 MILESTONE: RELEASE 1 COMPLETE — Car Master + Qualifications + Contracts + Assignments/Releases. Core asset management operational. |  |  |
| --- | --- | --- |

| RELEASE 2: SHOP OPERATIONS (Sprints 7-12 ¦ Weeks 13-24) |  |  |
| --- | --- | --- |

| SPRINT 7 ¦ Weeks 13-14 ¦ Shopping Event Engine |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Shopping event data model: shopping ID, car link, 6 types, reason, scope, status. Links to contract, project, shop. | Dev 1 (BE) | shopping_events table. Relationships to cars, leases, shops. CRUD API. |
| Shopping state machine: 13 states (Authorized → Closed). Transition rules, validation, timestamp tracking. | Dev 1 (BE) | ShoppingStateMachine service. Transition guards. Status history logging. |
| Shopping packet assembly: scope of work + project files + car data + commodity/cleaning. Auto-build. | Dev 2 (BE) | ShoppingPacketService: assemble_packet(). Pulls from car master, lease rider, project docs. |
| Commodity / cleaning auto-population: commodity from active rider. Cleaning class from AITX matrix. | Dev 2 (BE) | CommodityService: get_cleaning_requirements(). Commodity-to-cleaning mapping table. |
| Shopping creation UI: select car → auto-populate → tag type/reason → build scope → select shop (RailSync). | Dev 3 (FE) | ShoppingCreateWizard: Car → Details → Scope → Shop Selection → Review → Send. |
| Shopping summary dashboard: all active shoppings. Filter by shop, customer, type, status. Pipeline view. | Dev 3 (FE) | ShoppingDashboard: KPI cards, status pipeline, filterable table. |
| Shopping QA: creation flow, state transitions, packet assembly validation. | UI/QA Mgr | State transition matrix test. Packet completeness validation. |

| SPRINT 8 ¦ Weeks 15-16 ¦ Shopping Workflow + Communication |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Communication system: internal comments vs shop-facing. Visibility controls. Audit trail with timestamps. | Dev 1 (BE) | shopping_comments table. Visibility flag (internal/external). Ordered by timestamp. |
| Email integration: shopping packet email to shops. Configurable recipients. Attachments. Delivery tracking. | Dev 1 (BE) | EmailService: send_shopping_packet(). Template engine. Delivery status tracking. |
| Shopping status management: arrival, ship dates, POD tracking, outbound disposition. Batch status update. | Dev 2 (BE) | Status update endpoints. POD tracking with overdue alerting. Batch update for multiple cars. |
| Duplicate/copy shopping: template-based batch creation. Copy scope, projects, docs. Per-car validation. | Dev 2 (BE) | DuplicateShoppingService: copy_from_template(). Validates unique requirements per car. |
| Shopping detail view: all tabs (commodity, comments, projects, financials, status, files, email history). | Dev 3 (FE) | ShoppingDetail page: 8 tabs. Real-time status timeline. Comment thread UI. |
| Status management UI: update statuses with date pickers. POD tracking. Disposition selection. | Dev 3 (FE) | StatusUpdatePanel. PODTracker component. DispositionSelector. |
| Shopping workflow QA: end-to-end from creation to completion. Email delivery testing. | UI/QA Mgr | Full lifecycle test: create → send packet → arrive → estimate → complete. Email verification. |

| SPRINT 9 ¦ Weeks 17-18 ¦ Projects (Engineering) |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Project data model: project ID (EP series), type, status, engineer, description, spec, betterment, expense. | Dev 1 (BE) | projects table. CRUD API. Project-to-car many-to-many. |
| Project car assignment + document management: car lists, Box integration for repair instructions. | Dev 1 (BE) | project_cars table. Document reference linking to Box paths. |
| Project shop approval: shops approved per project. RailSync integration — ineligible shops filtered automatically. | Dev 2 (BE) | project_approved_shops table. RailSync rule engine filter: project_shop_eligible rule added. |
| Project → Shopping integration: auto-attach project files, validate shop eligibility when shopping created. | Dev 2 (BE) | Hook: on_shopping_create → check project eligibility → attach project docs to packet. |
| Project management UI: create/edit, assign cars (bulk), attach docs, approve shops. | Dev 3 (FE) | ProjectManagement page. ProjectDetail with tabs: Cars, Documents, Approved Shops, Shopping History. |
| Project → Shopping link UI: project files visible in shopping creation. Eligibility warnings displayed. | Dev 3 (FE) | ProjectFilesPanel in ShoppingCreateWizard. IneligibleShopWarning component. |
| Project QA: car assignment, document linking, shop eligibility validation. | UI/QA Mgr | Test: assign car to project → create shopping → verify docs attached and shop filtered. |

| 🏁 MILESTONE: SHOPPING OPERATIONAL — Full shopping lifecycle from authorization to completion. Projects integrated. Replaces CIPROTS Shopping + Projects. |  |  |
| --- | --- | --- |

| SPRINT 10 ¦ Weeks 19-20 ¦ BRC Processing + Estimate Approval |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| BRC import engine: parse 500-byte standard format. Match to shopping event by car/shop/date. | Dev 1 (BE) | BRCImportService: parse_500byte(). Matching algorithm. Import queue. |
| Estimate review engine: line-by-line display. Tag lessee responsibility. Approve/reject/negotiate per line. | Dev 1 (BE) | EstimateReviewService: tag_responsibility(), approve_line(), reject_line(). Bulk range update. |
| Revision tracking: versions (v1, v2, v3). Highlight changes. Carry forward responsibility codes. Time SLAs. | Dev 2 (BE) | estimate_revisions table. Diff calculation. SLA timer service. |
| Chargeback generation: auto-generate lessee chargeback BRC and 500-byte file from tagged responsibility. | Dev 2 (BE) | ChargebackService: generate_chargeback_brc(). 500-byte file generator. |
| BRC viewer UI: line-by-line controls. Responsibility tagging. Bulk operations. Revision comparison. | Dev 3 (FE) | BRCViewer component. LineItemGrid with approve/reject buttons. RevisionCompare modal. |
| Estimate approval UI: approval queue, escalation indicators, SLA countdown timers. | Dev 3 (FE) | EstimateApprovalQueue page. ApprovalCard with timer. EscalationBadge. |
| BRC QA: 500-byte parsing accuracy, line-by-line approval flow, revision comparison. | UI/QA Mgr | Test with real BRC samples. Verify parsing accuracy. Revision diff accuracy. |

| SPRINT 11 ¦ Weeks 21-22 ¦ Invoice Reconciliation + Cost Allocation |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Invoice match engine: auto-match invoice to approved estimate. Tolerance rules ($100 variance). | Dev 1 (BE) | InvoiceMatchService: auto_match(). Tolerance config. Result: auto-push, block, or exception. |
| Exception queue: blocked invoices with categorized errors. Resolution suggestions. Duplicate detection. | Dev 1 (BE) | invoice_exceptions table. Error categorization. Resolution workflow. |
| Cost allocation to SPV: automated allocation based on ownership. Multi-entity (AITX, ITE, Enkay). SAP payload. | Dev 2 (BE) | CostAllocationService: allocate_to_spv(). SAP push payload generator with line-item detail. |
| Railroad BRC processing: separate path for running repairs. No pre-auth. Auto-create MRU shopping. | Dev 2 (BE) | RailroadBRCService: process_rr_brc(). Auto-create shopping_event with type=MRU. |
| Invoice admin UI: approval queue, chargeback vs total validation, exception resolution. | Dev 3 (FE) | InvoiceAdmin page. ApprovalQueue tab. ExceptionResolver tab. One-click approve. |
| Exception resolution UI: error list with filters, click-to-resolve, audit trail. | Dev 3 (FE) | ExceptionList with error details. ResolutionDialog. HistoryPanel. |
| Invoice QA: auto-match accuracy, tolerance rules, SPV allocation validation. | UI/QA Mgr | Test scenarios: perfect match, under, over ($99 vs $101), line mismatch, MRU. |

| SPRINT 12 ¦ Weeks 23-24 ¦ Release 2 Integration + Stabilization |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Shopping → BRC → Invoice pipeline integration: end-to-end flow testing and bug fixes. | Dev 1 (BE) | Integration tests: shopping authorized → estimate loaded → approved → invoiced → allocated. |
| Data migration script v2: migrate active shopping events, BRC history, estimate approvals from CIPROTS. | Dev 2 (BE) | Migration: extract_ciprots_shopping.py. Map shopping types and statuses. |
| AI/ML estimate assistant: rule-based pre-review. Line-by-line accept/reject suggestions. Confidence scoring. | Dev 2 (BE) | EstimateAIService: pre_review(). Rule library. Confidence scores per line. (Phase 1 — rules only, ML later.) |
| Release 2 UI polish: shopping flow consistency, BRC viewer refinement, dashboard cohesion. | Dev 3 (FE) | UI review pass. Consistent patterns across shopping, BRC, invoice modules. |
| Release 2 regression testing: full QA pass. Shopping + BRC + Invoice end-to-end. | UI/QA Mgr | QA report. End-to-end scenario validation. Performance benchmarks. |
| Stakeholder demo: show complete shopping workflow from authorization through invoice close. | UI/QA Mgr | Demo: create shopping → send to shop → estimate → approve → invoice → allocated to SPV. |

| 🏁 MILESTONE: RELEASE 2 COMPLETE — Full shop operations: Shopping + Projects + BRC + Invoicing + Cost Allocation. Core CIPROTS operational replacement. |  |  |
| --- | --- | --- |

| RELEASE 3: BILLING + PLANNING + GO-LIVE (Sprints 13-18 ¦ Weeks 25-36) |  |  |
| --- | --- | --- |

| SPRINT 13 ¦ Weeks 25-26 ¦ Billing Engine |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Monthly rental invoicing: generate per contract. Pro-rata calculations. Pre-flight checks. | Dev 1 (BE) | BillingService: generate_monthly_invoices(). Pro-rata engine. Pre-flight validator. |
| Pending adjustments: auto-generated from lifecycle events (release, renewal, shop). Approval workflow. | Dev 1 (BE) | AdjustmentService: generate_from_event(). Approval queue. Must-clear enforcement. |
| Mileage processing: Railinc file ingestion, reconciliation, staging. Replace 27-step manual process. | Dev 2 (BE) | MileageService: ingest_railinc_file(), reconcile(), stage(). Automated pipeline. |
| Chargeback invoicing: generate from approved BRCs. One per customer. 500-byte auto-attachment. | Dev 2 (BE) | ChargebackInvoiceService: generate_invoices(). 500-byte attachment. Customer grouping. |
| Invoice distribution: automated email delivery. Contacts from Salesforce. Bounce handling. | Dev 2 (BE) | InvoiceDistributionService: send_invoices(). Template per customer. Delivery tracking. |
| Billing dashboard UI: month-end orchestration. Pre-flight status. Batch generation. Download/review tabs. | Dev 3 (FE) | BillingDashboard: PreFlightChecklist, BatchGenerator, ReviewTabs (Contracts, Adjustments, Mileage). |
| Pending adjustments UI: review, approve, reject. Filter by type. Batch approve. | Dev 3 (FE) | AdjustmentsQueue page. AdjustmentDetail with approve/reject. BatchApprove action. |
| Billing QA: monthly invoice generation, adjustment calculations, mileage processing. | UI/QA Mgr | Full month-end simulation. Compare outputs to CIPROTS for validation. |

| SPRINT 14 ¦ Weeks 27-28 ¦ SAP Integration + External Systems |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| SAP push: approved costs with SPV allocation and line-item detail. | Dev 1 (BE) | SAPIntegration: push_approved_costs(). Payload format per SAP requirements. Error handling + retry. |
| SAP push: billing triggers — rental invoices, adjustments, chargebacks for accounts receivable. | Dev 1 (BE) | SAPIntegration: push_billing_triggers(). Batch and real-time modes. |
| Salesforce integration: pull customer master, contacts, deal stages. Scheduled sync. | Dev 2 (BE) | SalesforceSync: pull_customers(), pull_contacts(). Scheduled job. Conflict resolution. |
| SAP push: mileage invoices and cash application data. | Dev 2 (BE) | SAPIntegration: push_mileage(). Cash application data format. |
| CLM / Telegraph API: car location data. Read current positions. (Phase 1 — read only.) | Dev 2 (BE) | CLMIntegration: get_car_locations(). Scheduled sync. Location history. |
| Integration monitoring UI: sync status, last run, error counts, retry controls. | Dev 3 (FE) | IntegrationMonitor page: status cards per system, error log, manual retry buttons. |
| Invoice history UI: posted invoices and credit memos. Search. PDF resend capability. | Dev 3 (FE) | InvoiceHistory page: searchable list, detail view, resend action. |
| Integration QA: SAP payload validation, Salesforce sync accuracy, error handling. | UI/QA Mgr | Mock SAP/SF endpoints for testing. Payload schema validation. Error scenario tests. |

| 🏁 MILESTONE: BILLING + INTEGRATIONS OPERATIONAL — Monthly billing works end-to-end. SAP receives data. Salesforce synced. |  |  |
| --- | --- | --- |

| SPRINT 15 ¦ Weeks 29-30 ¦ Planning & Forecasting (S&OP) |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Demand management: flexible demand types, monthly volume grid, constraints per demand. Import. | Dev 1 (BE) | demands table. CRUD API. CSV import. Flexible type system. |
| Allocation engine: run RailSync evaluateCar() in batch for demand forecasts. Monthly capacity tracking. | Dev 1 (BE) | AllocationService: run_allocation(). Monthly shop capacity buckets. Capacity decrement on allocation. |
| Scenario comparison: same rigor as shop comparison — all 25 rules, all cost variables. Custom weights. | Dev 2 (BE) | ScenarioService: compare_scenarios(). Pre-built templates. Custom weight configuration. |
| 18-month loading plan: shop × month grid. AITX internal + 3P networks. Utilization tracking. | Dev 2 (BE) | LoadingPlanService: generate_plan(). Monthly utilization calculation. |
| Demand grid UI: monthly entry, flexible categories, volume editing, CSV import. | Dev 3 (FE) | DemandGrid page: editable grid, category management, import dialog. |
| Planning grid UI: shop × month allocation grid. Capacity utilization bars. Summary rows. | Dev 3 (FE) | PlanningGrid page: interactive grid, utilization visualization, drag-and-drop (later). |
| Scenario builder UI: weight sliders, side-by-side comparison, apply scenario action. | Dev 3 (FE) | ScenarioBuilder: weight sliders, comparison table, ApplyScenario button. |
| Planning QA: allocation accuracy, scenario comparison consistency, capacity tracking. | UI/QA Mgr | Test: create demand → run allocation → verify capacity decrements → compare scenarios. |

| SPRINT 16 ¦ Weeks 31-32 ¦ Reporting + Analytics |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Fleet operations dashboard: KPIs (in shop, pending, at risk, qual status, utilization). Real-time. | Dev 1 (BE) | DashboardService: calculate_kpis(). Aggregation queries. Cache layer for performance. |
| Cost analytics: actual vs estimated by shop. Trends. Budget vs actual. Variance reporting. | Dev 1 (BE) | CostAnalyticsService: variance_report(), trend_analysis(). Historical comparison. |
| Shop performance: cycle time, defect rates, OTD, cost performance. Feed scoring model. | Dev 2 (BE) | ShopPerformanceService: calculate_metrics(). Historical data feeds RailSync scoring. |
| Configurable report builder: user-defined reports. Export to PDF/Excel. Scheduled distribution. | Dev 2 (BE) | ReportBuilder: template system, filter configuration, export engine, email scheduler. |
| Operations dashboard UI: KPI cards, charts, qualification calendar, shop utilization heatmap. | Dev 3 (FE) | OperationsDashboard: real-time KPIs, recharts visualizations, filter controls. |
| Cost analytics UI: variance charts, trend lines, budget tracker, drill-down by shop/customer. | Dev 3 (FE) | CostAnalytics page: interactive charts, period selectors, drill-down tables. |
| Notification system: email + in-app alerts. Qualification warnings, SLA breaches, exceptions. | Dev 1 (BE) | NotificationService: send_email(), create_in_app(). User preference management. |
| Reporting QA: KPI accuracy validation, report export formatting, notification delivery. | UI/QA Mgr | Cross-validate KPIs with manual calculations. Report format testing across browsers. |

| SPRINT 17 ¦ Weeks 33-34 ¦ Data Migration + Parallel Run Prep |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Data migration: full CIPROTS car master extraction. 150K cars mapped to permanent identity model. | Dev 1 (BE) | Migration pipeline: extract → transform → validate → load. Reconciliation report. |
| Data migration: contracts, riders, car assignments. Rate history. Active and recent-year data. | Dev 1 (BE) | Contract migration: map CIPROTS master/rider to new schema. Validate car-to-lease links. |
| Data migration: shopping events, BRC history, estimate approvals. Active + 2-year history. | Dev 2 (BE) | Shopping migration: map types, statuses, financials. BRC line-item migration. |
| Data migration: qualifications from CIS. Component serial numbers. Inspection history. | Dev 2 (BE) | Qualification migration: map CIS fields to new schema. Component serial validation. |
| Parallel run tooling: side-by-side comparison engine. Auto-compare CIPROTS vs RailSync outputs. | Dev 2 (BE) | ParallelRunService: compare_invoices(), compare_statuses(). Discrepancy report. |
| Data migration validation UI: reconciliation dashboards, record counts, discrepancy reports. | Dev 3 (FE) | MigrationDashboard: progress bars, reconciliation tables, error drill-down. |
| Migration QA: validate every migrated record category. Reconciliation against CIPROTS source. | UI/QA Mgr | Record count validation. Sample verification (100 random cars, 50 contracts, 50 shoppings). |

| SPRINT 18 ¦ Weeks 35-36 ¦ Parallel Run + Go-Live Prep |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Parallel run: run new system alongside CIPROTS. Compare billing outputs, BRC processing, status tracking. | All | 60-day parallel run begins. Daily discrepancy review. Issue triage. |
| Bug fixes + discrepancy resolution: address issues found during parallel run. | Dev 1+2 | P1 issues resolved within 24 hours. P2 within sprint. |
| User training: role-based training for Fleet Ops, Maintenance Coordinators, Billing, Engineering. | UI/QA Mgr | Training materials: video walkthroughs, quick reference guides, role-specific SOPs. |
| Training environment: sandbox with realistic data for hands-on practice. | Dev 3 (FE) | Training instance deployed. Seed data refreshed daily. User accounts provisioned. |
| Go-live runbook: step-by-step cutover plan. Rollback procedures. Support escalation contacts. | UI/QA Mgr | Runbook document. Tested rollback. War room plan for go-live week. |

| 🏁 MILESTONE: RELEASE 3 COMPLETE — Full CIPROTS replacement operational. Parallel run validates accuracy. Team trained. Ready for cutover. |  |  |
| --- | --- | --- |

| GO-LIVE + STABILIZATION (Sprints 19-20 ¦ Weeks 37-40) |  |  |
| --- | --- | --- |

| SPRINT 19 ¦ Weeks 37-38 ¦ CUTOVER WEEK + Stabilization |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Final data sync: last migration run to capture CIPROTS changes during parallel period. | Dev 1 (BE) | Delta migration: extract changes since last full migration. Apply + validate. |
| DNS/URL redirect: point users to new system. CIPROTS set to read-only archive. | Dev 2 (BE) | Cutover executed per runbook. CIPROTS access restricted to read-only. |
| Go-live support: war room for first week. Real-time issue triage and hotfix deployment. | All | War room active. Issue tracker monitored. Hotfix deployment pipeline tested. |
| User support: dedicated help channel. Quick-response for blocked users. | UI/QA Mgr | Support channel monitored. FAQ document updated daily based on common questions. |

| SPRINT 20 ¦ Weeks 39-40 ¦ Post Go-Live Stabilization |  |  |
| --- | --- | --- |
| Task | Owner | Deliverable |
| Performance tuning: address any scaling issues discovered under real production load. | Dev 1 (BE) | Query optimization. Index adjustments. Cache tuning based on real usage patterns. |
| Bug fixes: address issues found in first 2 weeks of production use. | Dev 1+2 | P1/P2 issues resolved. Known issues documented with workarounds. |
| User feedback integration: collect and triage enhancement requests from production users. | Dev 3 (FE) | Feedback collection. Prioritized backlog of enhancements. |
| Post-mortem + retrospective: document lessons learned, update processes, plan next phase. | UI/QA Mgr | Post-mortem document. Process improvements identified. V2 roadmap drafted. |

| 🏁 MILESTONE: CIPROTS REPLACED — RailSync Platform is the operational system of record for AITX Fleet Operations. |  |  |
| --- | --- | --- |

Key Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| SAP/Salesforce API access delayed by IT | Billing and customer data integration blocked. Release 3 delayed. | Start API access requests in Sprint 1. Build with mock adapters. Integration layer is swappable. |
| Data migration complexity from CIPROTS | Dirty data, unmapped fields, orphan records. Migration takes longer than planned. | Start migration scripts in Sprint 6. Iterative validation. Budget 2 extra weeks in parallel run. |
| Scope creep during stakeholder demos | New requirements surface. Sprint commitments at risk. | Strict change control after Sprint 6. New requests go to backlog. Demos show plan vs delivered. |
| BRC 500-byte format parsing edge cases | Real-world BRC files have variations not in spec. Invoice processing blocked. | Get 50+ real BRC samples from CIPROTS early. Build parser test suite before Sprint 10. |
| Team member turnover | Knowledge concentrated. Velocity drops if someone leaves. | Code reviews required on all PRs. Documentation standards enforced. No single-owner modules. |
| Parallel run discrepancies | New system and CIPROTS produce different results. Trust eroded. Go-live delayed. | Automated comparison tooling (Sprint 17). Daily discrepancy review. Root cause + fix protocol. |

Sprint Cadence & Ceremonies

•  Sprint Duration: 2 weeks (Monday to Friday)

•  Sprint Planning: Monday morning of sprint start (2 hours). Josh attends to validate priorities.

•  Daily Standup: 15 minutes. Blockers surfaced immediately.

•  Code Reviews: All PRs require 1 approval. No direct pushes to main.

•  Sprint Demo: Friday afternoon of sprint end. Stakeholders invited at milestone sprints (S2, S4, S6, S9, S12, S15, S18).

•  Retrospective: Friday after demo. Process improvements documented and acted on.

•  Release Gates: Each release requires QA sign-off, stakeholder approval, and Josh's go/no-go.

— End of Document —